## Sheet1
Task | StartDate | EndDate | DurationDays
Topic selection and proposal draft | 2025-10-15 | 2025-10-18 | 4
Initial reading / web research | 2025-10-19 | 2025-10-24 | 6
Literature review (core sources) | 2025-10-25 | 2025-10-31 | 7
Draft: background and basics | 2025-11-01 | 2025-11-05 | 5
Draft: caching section | 2025-11-06 | 2025-11-10 | 5
Draft: other techniques | 2025-11-11 | 2025-11-15 | 5
Methodology and example design | 2025-11-16 | 2025-11-20 | 5
Writing example and results | 2025-11-21 | 2025-11-26 | 6
First full report draft | 2025-11-27 | 2025-12-03 | 7
Revisions, figures, and polishing | 2025-12-04 | 2025-12-08 | 5
Final proofreading and submission | 2025-12-09 | 2025-12-11 | 3